## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 2 |  |  | Plan Duration | [5 empty] | Actual Start |  |  | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1) Model develeopment and parameterization | 1 | 4 | 1 | 0 | 0%
landscape extent and resolution | 1 | 1 | 1 | 0 | 0%
initial communities (SilviaTerra) | 1 | 3 | 1 | 0 | 0%
fire | 1 | 2 | 1 | 0 | 0%
insects | 1 | 2 | 1 | 0 | 0%
management | 1 | 2 | 1 | 0 | 0%
2) Modify extensions | 1 | 3 | 1 | 0 | 0%
improve bda by improving climate link | 1 | 3 | 1 | 0 | 100%
incorporating direct drought mortality | 2 | 3 | 2 | 0 | 0%
3) Scenario development (may be all handled by the May 21 meeting?) | 1 | 4 | 1 | 0 | 0%
4) Output generation | 3 | 3 | 3 | 0 | 0%
5) Reports/manuscripts | 6 | 6 | 6 | 0 | 0%
methods document | 1 | 9 | 1 | 0 | 0%
science briefs | 6 | 6 | 6 | 0 | 0%
draft manuscript | 8 | 5 | 8 | 0 | 0%